## Slide 1: In-Class Scheduling Exercise
Project Start Date: 5/1/2016
Code Value | Code Title
GC | General Contractor
PC | Plumbing Contractor
EC | Electrical Contractor
RC | Roofing Contractor
Activity | Description | Duration | Predecessor | Code
10 | Mobilization | 1 |  | GC
20 | Excavation | 2 | 10 | GC
30 | Place gravel | 2 | 20 | GC
40 | Place slab forms | 3 | 20 | GC
50 | Place rebar | 2 | 30 | GC
60 | Rough in plumbing | 2 | 50 | PC
70 | Pour & cure concrete | 9 | 40, 60 | GC
80 | Remove forms | 2 | 70 | GC
90 | Erect frame & sheath walls | 4 | 70 | GC
100 | Sheath roof | 3 | 80, 90 | RC
110 | Electrical | 3 | 100 | EC
120 | Install siding | 4 | 100 | GC
130 | Finish carpentry | 3 | 100 | GC
140 | Finish roof & flashing | 3 | 100 | RC
150 | Paint | 5 | 110, 120, 130 | GC
160 | Clean-up | 2 | 140, 150 | GC

## Slide 2: In-Class Scheduling Exercise
Draw the precedence diagram network
Use CPM calculations to determine the project duration
Develop a Gantt chart

## Slide 3: In-Class Scheduling Exercise
1. Draw the precedence diagram network
ES
Activity
EF
LS
LF
Dur.
Float
0
10
1
0
1
1
0
1
20
3
1
3
2
0
3
30
5
3
5
2
0
5
50
7
5
7
2
0
7
60
9
7
9
2
0
9
70
18
9
18
9
0
3
40
6
6
9
3
3

## Slide 4: In-Class Scheduling Exercise
1. Draw the precedence diagram network
ES
Activity
EF
LS
LF
Dur.
Float
9
70
18
9
18
9
0
18
80
20
20
22
2
2
22
100
25
22
25
3
0
25
110
28
26
29
3
1
29
150
34
29
34
5
0
34
160
36
34
36
2
0
18
90
22
18
22
4
0
25
120
29
25
29
4
0
25
130
28
26
29
3
1
25
140
28
31
34
3
6

## Slide 5: In-Class Scheduling Exercise
2. Determine the project duration
ES
Activity
EF
LS
LF
Dur.
Float
0
10
1
0
1
1
0
1
20
3
1
3
2
0
3
30
5
3
5
2
0
5
50
7
5
7
2
0
7
60
9
7
9
2
0
9
70
18
9
18
9
0
3
40
6
6
9
3
3

## Slide 6: In-Class Scheduling Exercise
2. Determine the project duration
ES
Activity
EF
LS
LF
Dur.
Float
9
70
18
9
18
9
0
18
80
20
20
22
2
2
22
100
25
22
25
3
0
25
110
28
26
29
3
1
29
150
34
29
34
5
0
34
160
36
34
36
2
0
18
90
22
18
22
4
0
25
120
29
25
29
4
0
25
130
28
26
29
3
1
25
140
28
31
34
3
6
Duration: 36 days
C.I. = # of Critical Act /
# of Total Act
= 11/16 = 0.69

## Slide 7: In-Class Scheduling Exercise
3. Develop a Gantt chart